●  SAMPLE — preview only. Not licensed for use. Buy the full editable file at impactmojo.in/products/tor-template/

Terms of Reference The complete commissioning pack: annotated template, question bank, scoring rubric, benchmarks and a worked example Template · DOCX · ₹199

Version 2.0   ·   June 2026   ·   Part of the Evaluation Essentials Kit

WHAT IS INSIDE THIS PACK Part A. How to commission well, in brief. Part B. The annotated terms of reference, thirteen sections, each with guidance, what good looks like, and the mistakes to avoid, plus space to write. Part C. Reference assets you would otherwise build from scratch: an evaluation question bank organised by the OECD-DAC criteria, a weighted bidder-scoring rubric, India-specific budget benchmarks, an indicative timeline, a glossary, and a short standards-and-sources list. Part D. A complete worked example: a filled ToR for a maternal and newborn health programme, the same case used across the ImpactMojo kit.

Replace every [bracketed prompt] and write on the ruled lines. Keep the grey guidance while drafting; delete it before you issue the document. A ToR is a contract brief and a thinking tool at once: the discipline of filling it well is most of the value.

PART A

Commissioning well, in brief

A terms of reference does three jobs at once. It forces you to decide what you actually need to know and why. It tells bidders precisely enough that their proposals are comparable. And it becomes the yardstick you hold the work against later. Thin ToRs fail at all three: they attract vague proposals, invite scope disputes mid-contract, and leave you with a report nobody can act on.

Three habits separate a ToR that works from one that wastes money.

- Start from the decision, not the study. Name the decision the evidence will inform, the person who will make it, and the date. If you cannot, you are buying a document, not evidence.

- Ask few, answerable questions. For every question, you should be able to name the data that would answer it. If you cannot, cut it or fund the data.

- Specify the standard of evidence you will accept. A causal claim needs a comparison group and a baseline, decided before rollout. Say so here, or do not ask for attribution later.

PART B

The annotated terms of reference

1.  Background and context

What this section is for.  Orient a competent outsider quickly: what the programme is, who funds and implements it, where and when it runs, and what problem it addresses.

Two or three short paragraphs. End with the single sentence that explains why this evaluation is being commissioned now. Attach the theory of change and logframe as annexes rather than narrating them here.

WHAT GOOD LOOKS LIKE Names the implementer, funder, geography, period, budget envelope, and the population reached, in under a page, and points to annexes for detail.

COMMON MISTAKES A history of the organisation. Bidders need the programme and its logic, not the institutional backstory.

2.  Rationale and timing: why now

What this section is for.  State the decision this evaluation will inform and when that decision is made.

Be concrete. “To inform the board’s March 2027 decision on whether to fund and scale a second phase” is a rationale; “to assess the programme” is not.

COMMON MISTAKES No decision attached, so the evaluation cannot be designed to be useful and the timeline floats.

3.  Purpose, objectives, intended use and users

What this section is for.  Separate the high-level purpose from the specific objectives, and name who will use the findings for what.

List three to five objectives at most. For each intended use, name the user and the action it informs (a funder’s scaling decision, a team’s redesign, a ministry’s policy).

WHAT GOOD LOOKS LIKE Each objective maps to at least one named user and a real decision, so nothing is measured that no one will use.

Purpose (one sentence)

Specific objectives:

- [Objective 1]

- [Objective 2]

- [Objective 3]

Primary users and the decisions they face

Name each user and what they will do with the findings.

— Sample ends here —  The full editable file (all sections, reference assets and a worked example) is delivered after purchase at impactmojo.in/products/tor-template/