## Slide 1
Introduction to MEL
Monitoring, Evaluation & Learning — the practitioner essentials
ImpactMojo · impactmojo.in · Free trainer deck (CC BY-NC-ND 4.0)
Notes: Welcome. This is a starter trainer deck from ImpactMojo. Adapt freely for your own workshops.

## Slide 2
What is MEL?
• Monitoring — tracking what you do and deliver, continuously
• Evaluation — judging whether it worked, and why, at points in time
• Learning — turning evidence into better decisions
• MEL exists to serve decisions, not to fill reports
ImpactMojo · impactmojo.in
Notes: Define each term. Stress that Learning is the point — data nobody uses is wasted.

## Slide 3
Monitoring vs Evaluation vs Learning
• Monitoring: routine, internal, 'are we on track?'
• Evaluation: periodic, often external, 'did it work & why?'
• Learning: reflection that changes what you do next
• All three draw on the same Theory of Change
ImpactMojo · impactmojo.in
Notes: Common confusion. A quick table on the board helps.

## Slide 4
Start with a Theory of Change
• Inputs → Activities → Outputs → Outcomes → Impact
• Make assumptions explicit at each link
• Indicators hang off the results chain
• If you can't draw it, you can't measure it
ImpactMojo · impactmojo.in
Notes: Sketch a simple results chain live with a programme the group knows.

## Slide 5
Indicators that work (SMART)
• Specific, Measurable, Achievable, Relevant, Time-bound
• Mix quantitative and qualitative
• Always plan disaggregation (gender, caste, age)
• Fewer, better indicators beat a long dashboard
ImpactMojo · impactmojo.in
Notes: Have participants critique a weak indicator and improve it.

## Slide 6
Data collection methods
• Surveys — breadth, comparability
• Interviews & FGDs — depth, the 'why'
• Administrative / MIS data — cheap, continuous
• Mixed methods triangulate; method follows the question
ImpactMojo · impactmojo.in
Notes: Match methods to the question type from the ToR.

## Slide 7
The MEL cycle
• Plan → Collect → Analyse → Report → Use → Adapt
• Build in reflection moments, not just reporting
• Budget for analysis and use, not only collection
• Close the loop: who acts on findings?
ImpactMojo · impactmojo.in
Notes: Emphasise 'Use' — the most skipped step.

## Slide 8
Common pitfalls
• Measuring activity, not change
• Too many indicators, no time to use them
• Collecting data nobody acts on
• Ethics & consent treated as an afterthought
ImpactMojo · impactmojo.in
Notes: Invite the group to name pitfalls they've seen.

## Slide 9
Go further with ImpactMojo
• MEL flagship course & MEL Design Lab
• Practice Packs: MEL from Scratch, Logframe, Survey, ToR
• Free templates: Logframe, MEL Plan, Budget, ToR
• impactmojo.in/catalog · impactmojo.in/products
ImpactMojo · impactmojo.in
Notes: Point to the free templates this deck ships with, and the Practice Packs.

## Slide 10
Thank you
impactmojo.in
Notes: Thanks. Share the templates and links.